## Sprint-1
Week #1 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
|  |  |  | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04
28
Exploring the tech-stack, gathering and analysing the requirements and creating diagrams to get idea about the project | Exploring different Technology stacks | Priyansh | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0
| Requirement Gathering and Analysis | All | 8 | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Architecture Diagram | Monil | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Class Diagram | Het | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Deployment Diagram | Parshv | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 0
| Database Schema Design | All | 8 | 8 | 6 | 4 | 3 | 2 | 1 | 0
|  | Actual | 30 | 30 | 25 | 21 | 12 | 10 | 5 | 0
Team: |  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Het Brahmbhatt | 7 hours / Week
Parshv Patel | 7 hours / Week
Monil Sakhidas | 7 hours / Week
Priyansh Patel | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-2
Week #2 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
|  |  |  | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11
28
Database design and deciding flow of the application through Wireframes | Database setup (MySQL(AWS RDS)) | Parshv | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Backend Setup (Node) | Monil | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Frontend Setup (React) | Het & Priyansh | 7 | 7 | 7 | 3 | 1 | 0 | 0 | 0
| Wireframes for Landing page, Login, Signup | Priyansh | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
| Wireframes for search flights, book tickets and cancel reservation | Het | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
| Wireframes for Admin Panel | Monil & Parshv | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Total | 28 | 25 | 21 | 14 | 12 | 9 | 4 | 0
Team: |  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Het Brahmbhatt | 7 hours / Week
Parshv Patel | 7 hours / Week
Monil Sakhidas | 7 hours / Week
Priyansh Patel | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-3
Week #3 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
|  |  |  | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18
28
Setting up few API's of Backend and initial pages of Frontend | Users, Flights and Reservations MySQL table creation (schema) | Parshv | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Setup passport.js and JWT Authentication | Priyansh | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Backend APIs for Signup and Login of Customers and Admins | Monil | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Backend API to Create Flights through Admin Panel | Parshv | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
| Backend APIs to View All Flights, View Flight details and View Flights created by self APIs through Admin Panel | Monil | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0
| Find a third party service that provides airport codes | Het | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Backend APIs to Search Airports and Search Flights | Het | 4 | 4 | 4 | 4 | 2 | 1 | 0 | 0
| Frontend for Home, LogIn, SignUp pages | Priyansh | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0
|  | Total | 29 | 27 | 23 | 18 | 10 | 7 | 2 | 0
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Het Brahmbhatt | 7 hours / Week
Parshv Patel | 7 hours / Week
Monil Sakhidas | 7 hours / Week
Priyansh Patel | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-4
Week #4 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
|  |  |  | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25
28
Developing Frontend and Backend | Frontend for Create Flights (Admin side) | Priyansh | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Frontend for View All Flights, View Flight details and View flights created by self (Admin side) | Parshv | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Frontend for Searching and booking flights | Monil | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Backend APIs to get effective price and create a reservation | Monil | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0
| Backend APIs to cancel a reservation and view all reservations | Het | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
| Frontend to Create a Reservation | Priyansh | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Frontend to view logged in user's reservations and cancel any future reservation | Het | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
| Backend API to view all reservations made by any customer throughout the system (Admin side) | Priyansh | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
| Frontend to view all reservations made by any customer throughout the system (Admin side) | Parshv | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0
|  | Total | 29 | 26 | 21 | 17 | 10 | 6 | 3 | 0
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Het Brahmbhatt | 7 hours / Week
Parshv Patel | 7 hours / Week
Monil Sakhidas | 7 hours / Week
Priyansh Patel | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-5
Week #5 (28 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
|  |  |  | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02
28
Testing, Deployment, Resolving Integration Errors and Wrapping up the work | Testing locally | All | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Minor Updations, Modifications & Integration | Monil | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0
| Minor Updations, Modifications & Integration | Priyansh | 4 | 4 | 4 | 2 | 1 | 0 | 0 | 0
| Minor Updations, Modifications & Integration | Het | 2 | 4 | 4 | 4 | 2 | 0 | 1 | 1
| Minor Updations, Modifications & Integration | Parshv | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Deployment | All | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0
| Testing on cloud | All | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Resolving Integration Errors | All | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Wrapping up the work | All | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Total | 28 | 29 | 26 | 21 | 15 | 9 | 4 | 1
Team: |  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Het Brahmbhatt | 7 hours / Week
Parshv Patel | 7 hours / Week
Monil Sakhidas | 7 hours / Week
Priyansh Patel | 7 hours / Week
Total Available Hours During Sprint: | 28